## Slide 1
PROJECT CHANGES
Kirsti Mijnhijmer, Joint Secretariat
1st October 2015 – Kuopio, Finland

## Slide 2: General Principles
Project managers are expected to manage project issues within their partnership. However, the implementation plan or budget may need to be revised.
Changes are divided into minor and major changes:
  The degree of the change will be determined by the JS
  Generally, projects are expected to have only one major change in their lifetime, and maximum one minor change request per reporting period.

## Slide 3: Minor changes
Budget changes below 60 000 EUR per project budget line, accumulated since the latest decision.
Implementation changes with no major impact on work plan, the project outputs, or results.
Travel outside the programme area, if not part of the application. Copenhagen = outside the area!
Minor administrative changes.
LP e-mails JS Desk Officer outlining the change, together with a justification and assessment of the impact on implementation and outputs.
Once pre-approved, the changes should be listed in the Progress Report confirming the picture that the changes are minor
Formal approval when approving the Activity Report. Latest decision remains valid for future reporting.

## Slide 4: Major changes
Budget changes above 60 000 EUR per project budget line, accumulated since the latest decision.
A change/withdrawal of partner
A change in the number/ character of main outputs or indicators
Implementation changes with a major impact on the work plan, the project outputs, or results.
An extension of eligibility period.
LP informs JS Desk Officer asap about the change, together with a justification and assessment of the impact on implementation and outputs
The Desk Officer may ask the LP to submit a revised application + supporting docs in eMS
The Desk Officer will make a decision proposal for MA or, if above 120 000 EUR, the Monitoring Committee
The MA issues a new decision

## Slide 5: Changes in eMS
In eMS, it is called ”modification request”  only for major changes
If needed, the JS will unlock the application, after which the LP can update it
The JS will compare both versions, and make a decision proposal. If MA/MC acceptance, the old application is replaced.

## Slide 6: Further guidance
JS Desk Officer and RCPs
Programme Manual:
  3.3.2. Changes in project implementation

## Slide 7: Thank you for listening
Kirsti Mijnhijmer
kirsti.mijnhijmer@interreg-npa.eu